## Instructions
		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

TEAM NAME	SSAD 17
PROJECT NAME	App8it
PROJECT MENTOR	Mr Nagarujuna( CEO Nag Enterprises)
TEAM MEMBERS	Aryaman Gupta
	Vatika Harlalka
	Shikha Jain
	Abhijeet kumar

## Team_Status
Week 14	App8it
	App8it
	Mr Nagarujuna

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 4
Role prefrences	Preparation	Vatika	1.5	1	Done		0.5	50
Git repository setup	Preparation	Abhijeet	0.25	0.25	Done		0	0
Develop questions for requiewments	Requirements	Aryaman	0.45	1	Delayed	Client Out of Station	-0.55	55
Initial Database Conceptual Design	Design	Vatika	1.5	4	Done		-2.5	62.5
Reseach existing frameworks	Requirements	Shikha	1.5	3	Done		-1.5	50
Project Synopsis WriteUp	Documentation	Aryaman	1.5	1	Done		0.5	50
Learn User Profiles and services	Preparation	Shikha,Aryaman	1.5	2	Done		-0.5	25
team meeting	Documentation	Abhijeet,Vatika,Shikha,Aryaman	1.5	2	Done		-0.5	25
status tracker	Documentation	Abhijeet	0.5	0.5	Done		0	0

Week 5
Learn php basics	Preparation	Aryaman	3.5	5	Done		-1.5	30
Understand Yii Basics	Preparation	Vatika	5	5	Done		0	0
Poject Plan Document Writeup	Documentation	Abhijeet	3	3	Done		0	0
Team Meeting	Coordination	Abhijeet	0.45	0.5	Done		-0.05	10
Update DB design	Design	Shikha	1.5	2	Done		-0.5	25
Make example app	Testing	Shikha,Vatika	3	4	Done		-1	25
Week 6
Create basic DB	Design	Abhijeet	2	3	Done		-1	33.3333333333
Basic Login	Development	Vatika	2	3	Done		-1	33.3333333333
Registration Admin , Developer, Analyst	Design	Shikha	1	1.5	Done
Registration User	Design	Aryaman	1	1.5	Done
status tracker	Documentation	Shikha	0.5	1	Done

Week 7
Basic bootstrap features	Development	Aryaman,Shikha	1.5	2	Done		-0.5	25
Database improvements	Design	Shikha	3	3	Done
Implementing RBAC	Development	Abhijeet,Vatika	5	7	Delayed	Database issuses not Resolved
Meeting minutes	Documentation	Abhijeet	0.5	0.5	Done
Populating database	Preparation	Aryaman,Vatika	3.5	3	Done

Week 8
Basic app testing	Testing	Abhijeet	2	2.5	Delayed		-0.5	20
Meeting minutes	Documentation	Vatika	0.5	0.5	Done
Design Document	Design	Abhijeet	3	2.5	Done
Implementing admin CRUDS	Requirements	Vatika,Shikha	3	5.5	Delayed	Problems With Yii
Bug removal	Development	Aryaman	1.5	3	Done		-1.5	50
status tracker	Documentation	Vatika	1	1.5	Done		-0.5	33.3333333333
Week 9
Frontend for Customer	Development	Abhijeet,Aryaman	3.5	5	Done		-1.5	30
Application tracking in the app	Requirements	Vatika	4	6	Done		-2
Testing and reporting Bug	Testing	Shikha	3	4.5	Done		-1.5
Implementing admin CRUDS	Development	Abhijeet	1	0.5	Done		0.5	100
Meeting minutes	Documentation	Vatika	0.5	0.5	Done
status tracker	Documentation	Vatika	1	1.5	Done		-0.5	33.3333333333
Bug Removal	Development	Aryaman	4	1.5	Done		2.5	166.6666666667
Week 10
Analsyt App view	Requirements	Vatika	3		Delayed	Inconsistent with clients' requirements
Analyst Approval rejection feaure	Requirements	Aryaman	2	2	Done		0	0
Admin App view	Requirements	Shikha	2	2	Done		0	0
Admin versions view	Requirements	Abhijeet	3	3	Delayed
status tracker	Documentation	Shikha	0.5	0.75	Done		-0.25	33.3333333333
Meeting minutes	Documentation	Vatika	0.5	0.5	Done
Admin Approval rejection feature	Requirements	Aryaman	2	2	Done		0	0
Week 11
Developer Versions view	Development	Vatika	3	4	Done		-1	25
Developer Applications view	Development	Abhijeet	3	3	Done		0	0
Developer Add new versions	Development	Shikha	2		Delayed	Inconsistent with clients' requirements
status tracker	Documentation	Shikha	0.5	1	Done		-0.5	50
Meeting minutes	Documentation	Vatika	0.5	0.5	Done

Developer create new app	Development	Aryaman	4	4	Done		0	0
Week 13
Category – Reveiwer Mapping	Development	Aryaman	3	3	Done		0	0
Admin : categories CRUD	Development	Vatika	2	2	Done		0	0
Admin : Checklist CRUD	Development	Shikha	2	3	Done		-1	33.3333333333
status tracker	Documentation	Shikha	0.5	1	Done		-0.5	50
Validations	Development	Abhijeet	5	6	Ongoing
Meeting minutes	Documentation	Vatika	0.5	0.5	Done
Developer Add new versions	Development	Shikha	2	4	Done		-2	50
Admin : Change password ( users')	Development	Aryaman	2	2	Done		0	0
Week 14
Delete : Soft delete	Requirements	Aryaman	2		Ongoing
History : Versions	Requirements	Shikha	2		Ongoing
status tracker	Documentation	Shikha	1		Ongoing
Validations	Development	Abhijeet	5		Ongoing
Testing	Testing	Abhijeet	4		Ongoing
Meeting minutes	Documentation	Vatika	0.5		Ongoing
Developer : Multimedia Upload	Requirements	Vatika	2		Ongoing
Week 15
Applications' Download Page	Development	Abhijeet			Planned
Categories' Page	Development	Aryaman			Planned
status tracker	Documentation	Shikha			Planned
Home page : Recontruction	Development	Shikha			Planned
Meeting minutes	Documentation	Vatika			Planned
Rate and Review feature	Development	Vatika			Planned
Week 16

## Individual_Status
Team Number	17
Poject Plan Document Writeup	App8IT
Team Meeting	Mr Nagarjuna

Actvities	Vatika Harlalka		Shikha Jain		Abhijeet Kumar		Aryaman Gupta		Estimated Total Hours	Actual Total Hours
	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent	Estimated Time	Actual Time Spent
Week 4 (aug 28 - sept 4th)
Role prefrences	1hour-2hours	1 hour					1 hour - 2hour	1 hour
Git repository setup					10-15 minutes	15 minutes			10-15 minutes	15 minutes
Develop questions for requiewments						30 minutes	1 hour	30 minutes - 1 hour	1 hour
Initial Database Conceptual Design	1 hour- 2hours	4 hours	1 hour - 2 hours	4 hours					1 - 2hours	4 hours
Reseach existing frameworks					1 - 2 hours	3 hours			1-2 hours	3 hours
Project Synopsis WriteUp						1 hour	1 hour	1-2 hours	1 hour
Learn User Profiles and services			1-2 hours	2 hours			1 - 2 hours	2 hours	1-2 hours	2 hours
team meeting	1-2 hours	2 hours	1-2 hours	2 hours	1-2 hours	2 hours	1-2 hours	2 hours	1-2 hours	2 hours
status tracker					30 minutes - 1 hour	30 minutes			30 minutes	30 minutes
Week 5 (sept 5- sept 11)
Learn php basics						3hours-4hours	5hours	3:30hours	5hours
Understand Yii Basics	4hours-6hours	5hours					4hours-6hours	5hours
Poject Plan Document Writeup					3hours	3hours			3hours	3hours
Team Meeting					30 minutes - 1 hour	30 minutes			30 minutes - 1 hour	30 minutes
Update DB design			1 hour - 2 hours	2 hours					1 hour - 2 hours	2hours
Make example app	1 hour- 2hours	2hours	1 hour - 2 hours	2hours					2hours – 4 hours	4 hours
Week 6 ( sept 12- sept19 )
Create basic DB	0	0	0	0	2hrs	3hrs	0	0	2hrs	3hrs
Basic Login	2hrs	3hrs					2hrs	3hrs
Registration Admin , Developer, Analyst			1hr	1hr					1hr	1hr
Registration User						1hr	1:30hr	1hr	1:30hr
status tracker			30minutes	1hour					30minutes	1hour

Week 7 (sept20 – sept27th)
Basic bootstrap features			30minutes	1hour	30 minutes - 1 hour	1hour			1.5hrs	2hrs
Database improvements			2hrs	3hrs					2hrs	3hrs
Implementing RBAC	1hr	2hr					4hr	5hours	5hrs	7hrs
Meeting minutes						30 minutes	30minutes	30 minutes	30 minutes
Populating database	1 hour- 2hours	1.5hrs			1hour	1.5 hrs			3hrs	3hrs

Week 8 (sept 28th – october 5th)
Basic app testing					2	2.5			2	2.5
Meeting minutes	0.5	0.5					0.5	0.5
Design Document					3	2.5			3	2.5
Implementing admin CRUDS	1	1.5	2	4					3	5.5
Bug removal						1.5	3	1.5	3
status tracker	1	1.5					1	1.5

Week 9 (5th october – 14th october)
Frontend for Customer					2	2.5	1.5	2.5	3.5	5
Application tracking in the app	4	6					0		4	6
Testing and reporting Bug			3	4.5					3	4.5
Implementing admin CRUDS					1	0.5			1	0.5
Bug Removal						4	1.5	4	1.5

0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0